## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-01 | Understand hospital revenue workflow and dataset | Must | Dataset availability | Shreeram Prajapati | Completed
S1 | S1 | US-01 | Perform data cleaning and preprocessing | Must | Raw dataset | Shreeram Prajapati | Completed
S1 | S1 | US-01 | Conduct exploratory data analysis (EDA) | Should | Cleaned dataset | Shreeram Prajapati | Completed
S2 | S2 | US-02 | View total billed vs collected revenue to monitor overall financial performance | Must | Data cleaning, KPI calculation | Shreeram Prajapati | Completed
S2 | S2 | US-03 | Track claim processing time to improve operational efficiency | Must | Date preprocessing, claim data availability | Shreeram Prajapati | Completed
S2 | S3 | US-02 | Calculate revenue leakage percentage to identify financial loss | Must | KPI formulas and payment data | Shreeram Prajapati | Completed
S3 | S3 | US-04 | Evaluate department-wise revenue performance to identify underperforming areas | Must | EDA and aggregation logic | Shreeram Prajapati | Completed
S3 | S3 | US-04 | Analyze claim trends within departments to detect problem areas | Should | EDA and trend analysis | Shreeram Prajapati | Completed
S3 | S3 | US-06 | Apply filters (date, department, insurer) to perform detailed analysis | Should | Dashboard UI components | Shreeram Prajapati | Completed
S3 | S4 | US-06 | Visualize data through dashboards, charts, and KPIs for easy interpretation | Must | Plotly & Streamlit integration | Shreeram Prajapati | Completed
S3 | S3 | US-05 | Identify high-risk claims before submission to prevent denials | Must | ML model (Logistic Regression) | Shreeram Prajapati | Completed
S3 | S4 | US-07 | Predict claim denial probability to proactively reduce revenue leakage | Must | ML model training & evaluation | Shreeram Prajapati | Completed
S4 | S4 | US-03 | Analyze claim denial patterns to reduce rejection rates | Must | Cleaned claim dataset | Shreeram Prajapati | Completed
S4 | S4 | US-05 | Monitor insurer-wise denial rates to manage payer-related risks | Must | Insurance data grouping | Shreeram Prajapati | Completed
S4 | S4 | US-07 | Assign risk scores to claims to prioritize high-risk cases | Should | Prediction model output | Shreeram Prajapati | Completed
S4 | S4 | US-03 | Monitor reimbursement cycle performance to optimize cash flow | Should | Settlement date and payment tracking | Shreeram Prajapati | Completed
S5 | S5 | US-05 | Generate alerts for high-risk or denied claims to enable timely action | Could | Risk scoring logic | Shreeram Prajapati | Completed
S5 | S5 | US-02 | Analyze high-level KPIs across all departments to support strategic decisions | Must | All KPI calculations | Shreeram Prajapati | Completed
S5 | S6 | US-04 | Compare performance across departments to benchmark efficiency | Should | Department-level aggregation | Shreeram Prajapati | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 49.5 | 5 | 7 | 9.5 | 10 | 7.5 | 6 | 3.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TASK-001 | Collect hospital dataset and understand columns | 2026-02-06 | 2026-02-07 | Shreeram Prajapati | Data Gathering | Completed | 1.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-002 | Check data types and structure | 2026-02-07 | 2026-02-08 | Shreeram Prajapati | Data Validation | Completed | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-003 | Handle missing values | 2026-02-08 | 2026-02-09 | Shreeram Prajapati | Data Cleaning | Completed | 1.5 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-004 | Prepare dataset (data types, formatting) | 2026-02-09 | 2026-02-10 | Shreeram Prajapati | Data Preprocessing | Completed | 1.5 | 0 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-005 | Basic EDA (revenue patterns) | 2026-02-11 | 2026-02-12 | Shreeram Prajapati | EDA | Completed | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-001 | TASK-006 | Build ML model for claim prediction | 2026-02-13 | 2026-02-15 | Shreeram Prajapati | ML Development | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-007 | Evaluate model performance | 2026-02-15 | 2026-02-16 | Shreeram Prajapati | Model Evaluation | Completed | 1.5 | 0 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-008 | Detect anomalies in billing data | 2026-02-16 | 2026-02-17 | Shreeram Prajapati | Anomaly Detection | Completed | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-009 | Build revenue forecasting model | 2026-02-17 | 2026-02-18 | Shreeram Prajapati | Forecasting | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-010 | Calculate financial KPIs | 2026-02-18 | 2026-02-19 | Shreeram Prajapati | Data Engineering | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-001 | TASK-011 | Create login and authentication | 2026-02-20 | 2026-02-21 | Shreeram Prajapati | Frontend | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-012 | Add navigation and sidebar | 2026-02-21 | 2026-02-22 | Shreeram Prajapati | Frontend | Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-013 | Build Executive dashboard | 2026-02-22 | 2026-02-24 | Shreeram Prajapati | Dashboard | Completed | 3 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-014 | Build Revenue Leakage page | 2026-02-24 | 2026-02-26 | Shreeram Prajapati | Dashboard | Completed | 2.5 | 0 | 0 | 0 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-015 | Build Risk & Anomaly pages | 2026-02-26 | 2026-02-28 | Shreeram Prajapati | Dashboard | Completed | 2.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-001 | TASK-016 | CFO dashboard and insights | 2026-03-01 | 2026-03-03 | Shreeram Prajapati | Dashboard | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-017 | Add insurance analytics | 2026-03-03 | 2026-03-05 | Shreeram Prajapati | Dashboard | Completed | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-018 | Add PDF export feature | 2026-03-05 | 2026-03-06 | Shreeram Prajapati | Feature | Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-019 | Improve UI and styling | 2026-03-06 | 2026-03-08 | Shreeram Prajapati | Styling | Completed | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
US-001 | TASK-020 | Integrate ML with dashboard | 2026-03-09 | 2026-03-12 | Shreeram Prajapati | Integration | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-021 | Fix bugs and improve filters | 2026-03-12 | 2026-03-14 | Shreeram Prajapati | Debugging | Completed | 2.5 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 6 BACKLOG
US-001 | TASK-022 | Final testing of all features | 2026-03-15 | 2026-03-20 | Shreeram Prajapati | Testing | Completed | 2.5 | 0 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-023 | Prepare documentation & presentation | 2026-03-20 | 2026-03-24 | Shreeram Prajapati | Documentation | Completed | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 2 | No clear understanding of hospital revenue workflow and project scope | Discussed with mentor in review meeting and finalized problem statement and approach
S1 | Day 5 | Large dataset (60k rows) causing slow loading and memory issues | Optimized data loading using pandas settings and handled data in smaller chunks
S2 | Day 9 | Null values affecting model training and calculations | Cleaned dataset by filling important missing values and removing highly incomplete records
S2 | Day 11 | Model performance was low in initial stage (poor prediction accuracy) | With mentor guidance, improved feature selection and added meaningful features which improved results
S3 | Day 16 | Issues in maintaining user session during dashboard navigation | Used session_state properly to store login and page details
S3 | Day 19 | Login system was not working consistently due to complex logic | Simplified authentication using basic Streamlit components after discussion with mentor
S3 | Day 22 | Charts were not displayed clearly and layout looked cluttered | Improved UI by restructuring chart placement and adding proper titles
S4 | Day 28 | PDF export was not capturing full dashboard content | Fixed by adjusting export settings and testing multiple times to capture full page

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-02-06 | 2026-02-12 | Shreeram Prajapati | Understanding hospital revenue domain and dataset | Took more time exploring data without clear focus | Planned tasks clearly and did daily tracking | Clear understanding of problem and project direction achieved
2 | S2 | 2026-02-13 | 2026-02-18 | Shreeram Prajapati | Building ML model and basic features | Model accuracy was low initially | Used better features and validation methods | Model performance improved (better prediction results)
3 | S3 | 2026-02-19 | 2026-02-24 | Shreeram Prajapati | Developing dashboard and login system | Faced issues in navigation and login handling | Used session_state for better control | Smooth login and page navigation achieved
4 | S4 | 2026-02-25 | 2026-03-02 | Shreeram Prajapati | Designing UI and adding charts | UI became complex and inconsistent | Simplified design and reused components | Clean and user-friendly dashboard created
5 | S5 | 2026-03-03 | 2026-03-12 | Shreeram Prajapati | Integrating ML models with dashboard | Difficulty connecting backend and frontend | Structured data flow properly | Successfully displayed predictions and insights in dashboard
6 | S6 | 2026-03-13 | 2026-03-24 | Shreeram Prajapati | Final testing and project completion | Minor bugs and performance issues | Fixed bugs and optimized performance | Final working project ready for presentation