## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Munavvara Nayab | 2026-02-07 | Login page not showing error when username/password is empty | S1 | Sourabh | UI | Added input validation using st.error() | 2026-02-08 | Closed | Fixed in login module
2 | Akshaya | 2026-02-09 | Incorrect revenue calculation causing negative leakage values | S1 | Vasundharadevi | Logical | Corrected formula for revenue leakage calculation | 2026-02-10 | Closed | Validated with sample data
3 | Saitej Barla | 2026-02-14 | Dashboard unable to load large dataset (performance issue) | S1 | Priyanka | Performance | Optimized using chunk reading and dtype handling | 2026-02-15 | Closed | Improved load time
4 | Sachin | 2026-02-18 | Claim processing time calculation incorrect due to date format issue | S2 | Shreeram Prajapati | Logical | Standardized date format and recalculated metrics, validate the integrity of healthcare claims data before it’s used for analytics, machine learning, & reporting | 2026-02-19 | Closed | Fixed in preprocessing
5 | Priyanka | 2026-02-20 | ML model giving low accuracy in claim denial prediction | S2 | Saitej Bharla | Model | Added feature engineering and improved training data | 2026-02-22 | Closed | Accuracy improved
6 | Mohammed Abdul Rehman Faadh | 2026-02-25 | Filters resetting when navigating between dashboard pages | S3 | Raghavi | Logical | Used session_state to persist filter values | 2026-02-26 | Closed | Fixed navigation issue
7 | Sourabh | 2026-02-27 | Role-based access not restricting department data properly | S3 | Prakhar Srivastava | Security | Applied department-level filtering logic | 2026-02-28 | Closed | Verified for all roles
8 | Deeparathna | 2026-03-01 | Charts overlapping with titles affecting readability | S3 | Sanyukta Kotale | UI | Moved titles outside charts using custom layout | 2026-03-02 | Closed | UI improved
9 | Prakhar Srivastava | 2026-03-05 | Prediction model returning null values for some inputs | S4 | Deeparathna | Model | Handled missing values before prediction | 2026-03-06 | Closed | Model stabilized
10 | Manonmayee Mellacheruvu | 2026-03-07 | Insurance analytics failing due to null date values | S4 | Munavvara Nayab | Logical | Added null checks before calculations | 2026-03-08 | Closed | Error resolved
11 | Soorabathula Sowmya | 2026-03-10 | PDF export capturing only partial dashboard view | S5 | Shanmugapriyadharshini | UI | Adjusted export to capture full page height | 2026-03-11 | Closed | Working across pages
12 | Raghavi | 2026-03-12 | Alerts not triggering for high-risk claims | S5 | Manonmayee Mellacheruvu | Logical | Fixed threshold condition for risk score | 2026-03-13 | Closed | Alerts working correctly
13 | Sarvadershita Maurya | 2026-03-18 | Department comparison showing inconsistent values | S6 | Harshit Sharma | Logical | Rechecked aggregation logic across departments | 2026-03-19 | Closed | Final validation done

## Sheet2
Logical
User Interface
Maintainability
Standards
Others